|  |  |  |  |
| --- | --- | --- | --- |
| **Task No** | **Tasks name** | **Depend** | **Duration** |
| **task 1** | customer request |  | **2 Days** |
| **task 2** | Appointment | T1 | **7 Days** |
| **task 3** | interview | T2 | **6 Days** |
| **task 4** | collect System | T3 (M1) | **11 Days** |
| **task 5** | Design initial plan | T4, T3 | **15 Days** |
| **task 6** | Time plan | T5(M2) | **6 Days** |
| **task 7** | Estimate cost | T 4, T 5 | **7 Days** |
| **task 8** | System analysis | T4, T5 | **4 Days** |
| **task 9** | Design database | T4 | **3 Days** |
| **task 10** | system design | T8 | **5 Days** |
| **task 11** | implementation | T10 (M3) | **23 Days** |
| **task 12** | Testing | T11 | 1. **Days** |

* ***Time plan:***